## turnover list
Turnover List
Ready for Marketing
Name | Subitems Material Sourcing Status | Subitems Received/Picked? | Material Sourcing | Notice Given | Move In | Tenants | Tenant Email 1 | Tenant Email 2 | Tenant Email 3 | Phone Number | Move-Out Date | Ameren LL | Nicor | Water | Forwarding Address | Move-Out Reason | General Property Condition- Kitchen | General Property Condition-Living Room | General Property Condition-Bathroom | General Property Condition-Bedroom 1 | General Property Condition-Other | Rating | Tenant Comments | Stage | Move-Out Checklist | MO Checklist Link | Send Owner Email | Turnover Start Date | Turnover completion date | Market Start Date | Lockbox Type/SN | Lawn | Sign | Interest | lockbox at property | Rent | Pictures | Turnover Status | Marketing Level | Property Type ↘️ | Stage due date | Stage Status | NTV Owner Email Sent? | Application | Mgmt. Agreement | Work Orders | WO Status | Billable hours so far | TCG $ invoiced Actual | Material $ invoiced Actual | Vendor $ invoiced Actual | *Maintenance hours estimate | % of Budget | *Turnover End Date | Market End Date | Current Days on Market | Completed days on Market | Creation log | People | Completed lost days | Open Lost days | Completed lost revenue | Open Lost Revenue | Open turnover duration | Completed turnover duration | Item ID | MO Inspections | Final Inspections | MO Insp Date | FI Date | Move Out Insp Link | Final Insp Link | Email Owner Estimate | Owner Estimate Email | Lockbox Location | Add Materials/Labor Jotform | Transcript Form | Weekly Progress Reports ¦ Turnovers | Walkthrough Status | Submitted Progress Reports | Turnover Staging | Total Labor | Staging Mirror | Units 🏡 | Owner Name | Owner Email 1 | Beds | Full Baths | Half Baths | OwnerEmail | Estimate Status | Change Order Status | Floorplan Status | Build Estimate | Build Change Order | Turnover Summary | Send Estimate | Approval TimeStamp | Link 1 | Owner email timestamp | Send CO Email | Most Recent CO description | HD Email | Menards Email | List Status | Build List | Home Depot List | Menards List | Route 6 Shop List | Other Material List | Leases 📑 | Calculate Costs | TCG Hours Calculation | Materials Calculated | Labor Rate | Total Est. Labor Cost | Total Est. Material Cost | Total Estimate TO Cost | Approve Est¦Create WO | ApproveCO¦Create WO | WO's Created | Sec Dep $ | Tenant Billed Labor | Tenant Billed Materials | CloseoutID | Closeout Status | link to closeout | Goal Date | Turnover Type | monday Doc v2 | Item ID 1
445 Elm Place L-23 Princeton IL 61356 |  |  |  | 2025-10-31 |  | Sandra Velazquez, Terra Lynn McCord |  |  |  |  | 2025-12-31 | v | v | v | 306 west morrell | [8 empty] | Keys Received |  |  | Send Email | 2025-12-31 | 2026-02-18 | [8 empty] | Ready To Market | Needs Marketing | Apartment | 2026-02-19 | In Range | Yes | Add |  | 445 Elm Place L-23 Princeton IL 61356TO/Tenant Billed, 445 Elm Place L-23 Princeton IL 61356TO/General Maintenance | Tech Closed, Tech Closed | 1.0, 1.0, 1.25, 3.12 |  | 0, 0 |  | 7 | 91 | 2026-02-18 |  |  |  | Oct 31, 2025 8:34 AM | Thalia |  | 50.7286 |  | 0 |  | 49 | 18318150792 | 1 | 1 | 2026-01-07 | 2026-02-18 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/y3R1odap8qX0xxZFy68DRXNMegBx0YzG | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/pqxEkdlgY1JVVVWiABgoDJZwPDbLWem3 | Click me | Not Sent |  | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18318150792%20-%20445%20Elm%20Place%20L-23%20Princeton%20IL%2061356&text_mkw2a9my=18318150792&text_mkw2sbhy=445%20Elm%20Place%20L-23%20Princeton%20IL%2061356 | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18318150792%20-%20445%20Elm%20Place%20L-23%20Princeton%20IL%2061356&text_mkw2a9my=18318150792&text_mkw2sbhy=445%20Elm%20Place%20L-23%20Princeton%20IL%2061356 |  | Not Done |  | 445 Elm Place L-23 Princeton IL 61356 | 1.0, 1.0, 1.25, 3.12 | 18318152180 | 445 Elm Place L-23 Princeton IL 61356 | Andrea C Nordstrom, Gentry Nordstrom, Hope Investments, LLC - Elm Place Series | andrea.nordstrom@gmail.com; andrea.nordstrom@gmail.com; gentry.nordstrom@gmail.com | 2 | 1 | 0 | gentry@thechrysalis.group | Approved |  | Picture in Rentvine | Build Estimate | Build Change Order | Turnover at **445 Elm Place L-23, Princeton, IL 61356** will address minor surface repairs and appearance items throughout the unit. Work includes patching ceiling nail pops and completing a small wall paint touch-up in the living room to restore a consistent finished look. In the kitchen, the scope focuses on cleanliness and sealing: the kitchen light fixture will be cleaned and the caulking behind the counter will be removed and replaced to improve sanitation and prevent moisture intrusion. The wall A/C unit will be cleaned (including coil/fin cleaner) to address odor; the estimate also includes a contingency to evaluate and replace the 220V wall A/C unit if needed. Living room window coverings will be replaced (middle and left blinds), with those costs billed back to the tenant. **Material cost:** $908.00 **Labor cost:** $239.30 **Total estimated cost:** $1,147.30 **Materials (itemized):** - Drywall patch compound/repair kit: $111.00 - Kitchen/bath caulk: $12.00 - Paint for touch-up (match existing): $35.00 - AC coil/fin cleaner: $8.00 - Wall AC unit – 220V: $680.00 - Blinds (replacement) (2 @ $31): $62.00 **Tenant bill-back (included above):** - Tenant billed labor: $65.00 - Tenant billed materials: $62.00 - Total tenant bill-back: $127.00 | Send Estimate to Owner |  |  | 2026-01-23 | Send CO Email |  | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | None | None | - 1 ea — Drywall patch compound/repair kit (SKU/Model: N/A) - 1 tube — Kitchen/bath caulk (SKU/Model: N/A) - 1 ea — Paint for touch-up (match existing) (SKU/Model: N/A) - 1 can — AC coil/fin cleaner (SKU/Model: N/A) - 1 ea — Wall AC unit - 220V (SKU/Model: N/A) - 2 ea — Blinds (replacement) (SKU/Model: N/A) |  | Cost Calculator | Calculated | Calculated | Nordstrom | 239.3 | 908 | 1147.3 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=18318150792&decision=approved | CO Manual Approval ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=18318150792&decision=approved | Yes |  | 65 | 62 | 11202511652 | Creating... | 445 Elm Place L-23 Princeton IL 61356 | 2026-02-02 | Light |  | 18318150792
|  |  |  | 2025-10-31 | [6 empty] | 2025-12-31 | 1/1 | 1/1 | 1/1 | [7 empty] | 0/5 | [5 empty] | 2025-12-31 | 2026-02-18 |  |  | 0/1 | 0/1 | 0/1 | 0/1 | =SUM(AK4:AK4) |  |  |  |  | 2026-02-19 | [10 empty] | =SUM(BA4:BA4) | 91 | 2026-02-18 |  | null | null |  |  | null | 50.7286 | no_numeric_values_available | 0 | null | 49 |  | =SUM(BP4:BP4) | =SUM(BQ4:BQ4) | 2026-01-07 | 2026-02-18 | [5 empty] | null | [23 empty] | 2026-01-23 | [15 empty] | =SUM(DM4:DM4) | =SUM(DN4:DN4) | 1147.3 |  |  |  | =SUM(DS4:DS4) | =SUM(DT4:DT4) | =SUM(DU4:DU4) |  |  |  | 2026-02-02
Fully Completed
Name | Subitems Material Sourcing Status | Subitems Received/Picked? | Material Sourcing | Notice Given | Move In | Tenants | Tenant Email 1 | Tenant Email 2 | Tenant Email 3 | Phone Number | Move-Out Date | Ameren LL | Nicor | Water | Forwarding Address | Move-Out Reason | General Property Condition- Kitchen | General Property Condition-Living Room | General Property Condition-Bathroom | General Property Condition-Bedroom 1 | General Property Condition-Other | Rating | Tenant Comments | Stage | Move-Out Checklist | MO Checklist Link | Send Owner Email | Turnover Start Date | Turnover completion date | Market Start Date | Lockbox Type/SN | Lawn | Sign | Interest | lockbox at property | Rent | Pictures | Turnover Status | Marketing Level | Property Type ↘️ | Stage due date | Stage Status | NTV Owner Email Sent? | Application | Mgmt. Agreement | Work Orders | WO Status | Billable hours so far | TCG $ invoiced Actual | Material $ invoiced Actual | Vendor $ invoiced Actual | *Maintenance hours estimate | % of Budget | *Turnover End Date | Market End Date | Current Days on Market | Completed days on Market | Creation log | People | Completed lost days | Open Lost days | Completed lost revenue | Open Lost Revenue | Open turnover duration | Completed turnover duration | Item ID | MO Inspections | Final Inspections | MO Insp Date | FI Date | Move Out Insp Link | Final Insp Link | Email Owner Estimate | Owner Estimate Email | Lockbox Location | Add Materials/Labor Jotform | Transcript Form | Weekly Progress Reports ¦ Turnovers | Walkthrough Status | Submitted Progress Reports | Turnover Staging | Total Labor | Staging Mirror | Units 🏡 | Owner Name | Owner Email 1 | Beds | Full Baths | Half Baths | OwnerEmail | Estimate Status | Change Order Status | Floorplan Status | Build Estimate | Build Change Order | Turnover Summary | Send Estimate | Approval TimeStamp | Link 1 | Owner email timestamp | Send CO Email | Most Recent CO description | HD Email | Menards Email | List Status | Build List | Home Depot List | Menards List | Route 6 Shop List | Other Material List | Leases 📑 | Calculate Costs | TCG Hours Calculation | Materials Calculated | Labor Rate | Total Est. Labor Cost | Total Est. Material Cost | Total Estimate TO Cost | Approve Est¦Create WO | ApproveCO¦Create WO | WO's Created | Sec Dep $ | Tenant Billed Labor | Tenant Billed Materials | CloseoutID | Closeout Status | link to closeout | Goal Date | Turnover Type | monday Doc v2 | Item ID 1
445 Elm PL Apt R12 | Ordered, Ordered, Ordered, Ordered, Priced | Not Picked, Not Picked, Not Picked, Not Picked | Ordered, Ordered, Ordered, Ordered, Priced | 2025-08-29 | 2025-11-03 | Andrew Kurtenbach | atkurtenbach@gmail.com | atkurtenbach@gmail.com | atkurtenbach@gmail.com | 12172570685 | 2025-09-30 |  |  |  | 1409 N Kennedy Dr #B | Relocated for work | https://tcg356580.monday.com/protected_static/14862391/resources/2477700835/20250829_025110.jpg, https://tcg356580.monday.com/protected_static/14862391/resources/2477700839/20250829_025121.jpg | https://tcg356580.monday.com/protected_static/14862391/resources/2477700901/20250829_025144.jpg, https://tcg356580.monday.com/protected_static/14862391/resources/2477700908/20250829_025154.jpg | https://tcg356580.monday.com/protected_static/14862391/resources/2477700951/20250829_025219.jpg | https://tcg356580.monday.com/protected_static/14862391/resources/2477700982/20250829_025251.jpg, https://tcg356580.monday.com/protected_static/14862391/resources/2477700984/20250829_025300.jpg | https://tcg356580.monday.com/protected_static/14862391/resources/2477701015/20250829_025312.jpg, https://tcg356580.monday.com/protected_static/14862391/resources/2477701021/20250829_025322.jpg | 4 |  | Waiting On Keys | https://tcg356580.monday.com/protected_static/14862391/resources/2477700804/445%20Elm%20PL%20Apt%20R12.pdf | Move-Out Checklist - https://superform.spot-nik.com/instance/92e37e509633464ea58a8e7314a29c85 | Send Email | 2025-10-01 | 2025-11-03 |  | NA | [6 empty] | Ready To Market | Deposit Received | Apartment |  |  | No | Add |  | 445 Elm Place Unit R12, 445 Elm Place Unit R12, 445 Elm Place Unit R12 | Completed, Completed, Completed | 1.12, 8.0, 3.83 | 530 | 184, 0, 0 | 0 | 22 |  | 2025-11-03 | 2025-11-03 |  |  | Oct 10, 2025 8:23 AM | Thalia | 34 |  | 0 |  |  | 33 | 18157316511 | 1 |  | 2025-10-06 |  | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/YwV91eKlayDJo44guEW5l7ZomOLnBvq0 |  | Click me | Not Sent | NA | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18157316511%20-%20445%20Elm%20PL%20Apt%20R12&text_mkw2a9my=18157316511&text_mkw2sbhy=445%20Elm%20PL%20Apt%20R12 | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18157316511%20-%20445%20Elm%20PL%20Apt%20R12%20(copy)&text_mkw2a9my=18157316511&text_mkw2sbhy=445%20Elm%20PL%20Apt%20R12%20(copy) | 445 Elm PL Apt R12 | Not Done | 2025-10-31 | 445 Elm PL Apt R12 (copy), 445 Elm PL Apt R12 | 3.83, 1.12, 8.0, 3.83, 1.12, 8.0 | 18157318837, 18233484437 | [6 empty] | gentry@thechrysalis.group | Approved |  | Not Done | Build Estimate | Build Change Order | The turnover at 445 Elm PL Apt R12 will address general repairs, cleaning, and cosmetic updates throughout the unit. In the bathroom, entry, bedrooms, living room, and hallway we’ll repair door interiors, chain locks, and toilet paper holders; clean light fixtures; replace the smoke detector and outlet covers; and remove chipped paint, old shelving, curtains, and any leftover personal items. New window blinds will be installed in both bedrooms and the living room, sized to fit and sourced from Menards. Walls and vents showing wear will receive paint touch-ups and, where needed, full repaints using color-matched paint. These improvements restore safety, functionality, and aesthetics, ensuring the unit meets move-in standards. Costs: • Material cost: $282 • Labor cost: $650 • Total cost: $932 Materials: • Hallway smoke detector: $52.50 • Blind – 22 x 58: $26.50 • Blind – 22 x 58: $26.50 • Blind – 23 1/2 x 58: $26.50 • Paint (2 gallons): $150.00 | Send Estimate to Owner |  |  | 2025-10-13 | Send CO Email |  | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | - Source the hallway smoke detector: 1 ea - Blind – 22 × 58: 1 ea - Blind – 22 × 58: 1 ea - Blind – 23 1/2 × 58: 1 ea | None | - Paint (Sherwin) – 2 ea |  | Cost Calculator | Calculated |  | Nordstrom | 650 | 282 | 932 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=18157316511&decision=approved |  | Yes | [6 empty] | 2025-10-30 |  |  | 18157316511
1444/4 State Street |  |  |  | 2025-09-15 | 2025-12-23 | [5 empty] | 2025-09-30 | [12 empty] | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/577226e058554fe19ee6ef1a85276c38 | Send Email | 2025-10-02 | 2025-11-03 | 2025-11-03 | NA |  |  |  |  | 1600 | New Pictures In Rentvine | Ready To Market | Deposit Received | Furnished - Medium Term |  |  | No | Add | Full Service | 1444 Catherine St unit 4 | Completed | 1.38, 1.08 |  | 0 |  | 5 |  | 2025-11-03 | 2025-12-18 | 108.7286 | 45 | Oct 10, 2025 8:24 AM | Thalia | 84 |  | 4480 |  |  | 32 | 18157327495 | 1 | 1 | 2025-10-02 | 2025-10-30 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/QnN2z9K3xd47OEEnhVZ3prMPOV0lDaq5 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/k3pvoQ4ae6XWBBEFo2aq37DqO9NxnWlK | Click me | Not Sent | NA | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18157327495%20-%201444/4%20State%20Street&text_mkw2a9my=18157327495&text_mkw2sbhy=1444/4%20State%20Street | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18157327495%20-%201444%2F4%20State%20Street%20(copy)&text_mkw2a9my=18157327495&text_mkw2sbhy=1444%2F4%20State%20Street%20(copy) | 1444/4 State Street | Not Done | 2025-10-31 | 1444/4 State Street (copy), 1444/4 State Street | 1.38, 1.08, 1.08 | 18157328985, 18233482071 | [6 empty] | gentry@thechrysalis.group | Ready to Send |  | Picture in Rentvine | Build Estimate | Build Change Order | At 1444/4 State Street, this turnover scope focuses on restoring unit functionality and appearance through minor repairs, sealing, and finishes. In the hallway and closets, technicians will remove old hangers, realign closet doors, and replace a lightbulb. Countertop adhesion will be reinforced, and small gaps in the bathroom will be sealed with caulk. In the right bedroom, broken tiles will be replaced and casing will receive a paint touch-up, using fresh white paint to ensure a consistent finish. Materials are also replenished: paint, caulk, subway tiles and a bulb to leave the unit fully stocked for ongoing upkeep. Costs Material Cost: $32 Labor Cost: $175 Total Cost: $207 Materials • Paint – white (1 gallon): $10 • Caulk (1 tube): $2 • Subway tiles (1 ea): $15 • Lightbulbs (1 ea): $5 | Send Estimate to Owner |  |  |  | Send CO Email |  | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | - Subway tiles: 1 ea | - Paint - white: 1 gallon - Caulk: 1 tube - Lightbulbs: 1 ea | None |  | Cost Calculator | Calculated | Calculated | Nordstrom | 175 | 32 | 207 |  |  | No | 1600 | [8 empty] | 18157327495
602/1B |  |  |  | 2025-09-05 | 2025-12-31 | Payton Blake Nighswonger |  |  |  |  | 2025-10-05 | [12 empty] | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/4573d93d026f4ac79425299a14f59b39 | Send Email | 2025-10-01 | 2025-12-09 | 2025-12-09 | 2296369- sentrilock |  |  |  |  | 900 | New Pictures In Rentvine | Ready To Market | Deposit Received | Apartment |  |  | No | Add | Full Service | 602/1BTO/Tenant Billed, 602/1BTO/Painting, 602/1BTO/General Maintenance | Completed, Completed, Completed | 1.58, 4.45, 3.6, 4.4, 2.73, 0.52, 7.92, 6.25, 7.95, 1.85, 1.63, 2.53, 4.23, 1.07, 6.33, 0.72, 3.2, 2.32 | 260, 2012.5 | 117, 0, 707 | 00, 000 | 12 |  | 2025-12-09 | 2025-12-19 | 72.7286 | 10 | Oct 8, 2025 12:47 PM | Thalia | 87 |  | 2610 |  |  | 69 | 18141151830 | 1 | 1 | 2025-10-07 | 2025-12-04 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/zPpqGxOn8BNr255Zujjy4X9LYy0mA4KQ | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/p61mxYzNaw78WWvfVVNGRJbo3gBne4GV | Click me | Not Sent | back railing by building door- parking lot side | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18141151830%20-%20602/1B&text_mkw2a9my=18141151830&text_mkw2sbhy=602/1B | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18141151830%20-%20602%2F1B%20(copy)&text_mkw2a9my=18141151830&text_mkw2sbhy=602%2F1B%20(copy) | 602/1B, 602/1B, 602/1B, 602/1B, 602/1B | Done | 2025-11-21, 2025-10-31, 2025-11-21 | 602/1B (copy), 602/1B (copy), 602/1B | 1.58, 4.45, 1.85, 1.63, 2.53, 4.23, 3.6, 4.4, 4.4, 2.73, 0.52, 7.92, 1.07, 6.25, 7.95, 6.33, 0.72, 3.2, 2.32, 4.45, 1.85, 1.63, 2.53, 4.23, 3.6, 4.4, 4.4, 2.73, 0.52, 7.92, 1.07, 6.25, 7.95, 6.33, 0.72, 3.2, 2.32, 4.45, 1.85, 1.63, 2.53, 4.23, 3.6, 4.4, 4.4, 2.73, 0.52, 7.92, 1.07, 6.25, 7.95, 6.33, 0.72, 3.2, 2.32 | 18141152582, 18157362288, 18233483144 | 602 E Mckinley Road Apt 1B Ottawa IL 61350 | Hope Investments, LLC | jnord107@aol.com | 2 | 1 | 0 | gentry@thechrysalis.group | Approved |  | Picture in Rentvine | Build Estimate | Build Change Order | The turnover for unit 602/1B will address all outstanding maintenance and aesthetic issues throughout the property. In the bathroom, the ceiling crack will be patched, caulking renewed, hardware tightened, stopper reinstalled, toilet seat replaced, exhaust fan cleaned and the furnace filter changed. General surface preparation—item removal, patching and cleaning—will be carried out in each room to ensure smooth, clean walls and trim ready for paint. A full repainting will refresh the bathroom, all bedrooms, the dining room, hallway, kitchen and living room, covering walls, doors, door casings, baseboards and cabinetry as needed. Additionally, non-working elements will be replaced: blinds and slats in the bedrooms, vertical blind slats, and a dining room light bulb. These actions restore function, improve appearance and ensure the unit is tenant-ready. Material Cost: $302 Labor Cost: $568 Total Estimated Cost: $870 Materials: - Trim paint (1 gallon): $35 - First Star paint (1 gallon): $50 - Light French gray paint (2 gallons): $100 - Toilet seat: $15 - Vertical blind slats (3 ea): $87 - Furnace filter: $15 | Send Estimate to Owner |  |  |  | Send CO Email |  | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | - Replace toilet seat: 1 ea - Vertical Blind Slats: 3 ea | None | - 1 gallon Trim paint - 1 gallon First Star paint - 2 gallon Light French gray paint - 1 ea Furnace filter |  | Cost Calculator | Calculated | Calculated | Nordstrom | 568 | 302 | 870 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=18141151830&decision=approved | CO Manual Approval ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=18141151830&decision=approved | Yes | 900 |  |  |  |  | 602/1B, 602/1B |  |  |  | 18141151830
606/2B |  |  |  | 2025-09-09 | 2026-01-14 | Sonia Gabriel Alonso Cortez |  |  |  |  | 2025-10-31 | [12 empty] | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/a95648d1c7914af283d9151ed16cd0ba | Send Email | 2025-10-02 | 2026-01-07 | 2026-01-07 | 2374831 sentrillock |  |  |  |  | 900 | New Pictures In Rentvine | Ready To Market | Deposit Received | Apartment |  | Overdue | No | Add | Full Service | 606/2BTO/Painting, 606/2BTO/Tenant Billed, 606/2BTO/General Maintenance, 606/2B/TO Final Maintenance, 606/2B/TO/Final Maintenance | Completed, Completed, Completed, Completed, Completed | 3.92, 0.82, 8.0, 3.77, 1.9, 0.83, 2.97, 2.63, 2.25, 0.53, 1.87, 3.12 | 195, 1308.65, 113.75 | 0, 885, 65.85, 0, 33.23 | 00000000, 000, 000 | 34.25 |  | 2026-01-07 | 2026-01-14 | 43.7286 | 7 | Oct 10, 2025 8:24 AM | Thalia | 75 |  | 2250 |  |  | 97 | 18157333153 | 1 | 1 | 2025-10-07 | 2026-01-02 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/4aLBOjwoQAVrAzzMuddjVJyNDWRnK8Y2 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/dyYW2jB9wVr5qqBfb10zerlq45zkRO1P | Click me | Not Sent | back of the building on railing to building | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18157333153%20-%20606/2B&text_mkw2a9my=18157333153&text_mkw2sbhy=606/2B | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18157333153%20-%20606%2F2B%20(copy)&text_mkw2a9my=18157333153&text_mkw2sbhy=606%2F2B%20(copy) | 606/2B, 606/2B, 606/2B, 606/2B, 606/2B, 606/2B, 606/2B, 606/2B, 606/2B | Done | 2025-11-21, 2025-10-31, 2025-11-21 | 606/2B (copy), 606/2B | 3.77, 2.63, 3.92, 0.82, 8.0, 1.9, 0.83, 2.97, 2.25, 0.53, 1.87, 3.12, 3.77, 2.63, 3.92, 0.82, 8.0, 1.9, 0.83, 2.97, 2.25, 0.53, 1.87, 3.12 | 18157334517, 18233483522 | [6 empty] | gentry@thechrysalis.group | Approved |  | Picture in Rentvine | Build Estimate | Build Change Order | The turnover at unit 606/2B addresses all necessary repairs, cleaning, and cosmetic updates to bring the apartment to market-ready condition. In the bathroom, we’ll clean fixtures, replace the showerhead and exhaust fan, re-caulk around the shower, sink, tub, and surround, and repaint walls, baseboards, door, and casing. The kitchen and living areas receive plumbing touch-ups (faucet aerator, appliance filter), cabinet and wall paint touch-ups, and general cleaning (light covers, carpet cleaning). Bedrooms will have dents and holes patched, new closet door hardware installed, blinds replaced, ceilings and walls repainted, and baseboards touched up. Common spaces including the entryway, hallway, and dining room will also be painted and baseboards freshened. Structural and finish repairs include drywall/plaster patching in bedrooms and the bathroom, replacement of the furnace filter, removal of leftover items from the systems closet, and repair of the living room screen. Hardware and miscellaneous installations cover removal of old towel racks and toilet paper holders, sourcing of new screen material and aerator, and installation of a new closet door. Material Cost: $1,070.00 Labor Cost: $1,381.50 Total Estimated Cost: $2,451.50 Materials - Trim paint (1 gal): $35.00 - “First Star” paint (1 gal): $50.00 - Light French Grey paint (2 gal): $100.00 - Closet door: $800.00 - Blind panels: $23.00 - Furnace filter: $22.00 - Door patch kit: $5.00 - Screen material: $23.00 - Faucet aerator: $12.00 | Send Estimate to Owner |  |  |  | Send CO Email |  | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com |  | Build Material List | [5 empty] | Cost Calculator | Calculated | Calculated | Nordstrom | 1381.5 | 1070 | 2451.5 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=18157333153&decision=approved | CO Manual Approval ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=18157333153&decision=approved | Yes | 900 | 4 | 6 |  |  | 606/2B, 606/2B, 606/2B |  |  |  | 18157333153
141 B East Walnut Street |  |  |  | 2025-10-08 | 2026-01-23 | Tim Keldgord | dewalttk17@gmail.com | dewalttk17@gmail.com | dewalttk17@gmail.com | 13192170738 | 2025-10-31 |  |  |  | 2584 south grand, Mount Pleasant, IA 52641 | moving for work | [5 empty] | 4 |  | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/54bb65978df14f2fbd351b8a396bc8de | Send Email | 2025-11-06 | 2026-01-12 | 2026-01-12 | 2369617-sentrilock |  |  |  |  | 1300 | New Pictures In Rentvine | Ready To Market | Deposit Received | Apartment |  | Overdue | No | Add | Full Service | 141 B East Walnut StreetTO/Tenant Billed, 141 B East Walnut StreetTO/Painting, 141 B East Walnut StreetTO/General Maintenance | Completed, Completed, Completed | 2.23, 2.5, 1.33, 1.13, 2.93, 2.83, 2.72, 2.25, 4.63, 2.05, 4.05, 2.62 | 1070.65, 390 | 84.05, 0, 20.65 | 00, 00 | 19.47 | 160.6061 | 2026-01-12 | 2026-01-14 | 38.7286 | 2 | Oct 8, 2025 12:45 PM | Thalia | 84 |  | 3640 |  |  | 67 | 18141131867 | 1 | 1 | 2025-11-06 | 2026-01-07 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/NWOVw9m6aDrQYY0HpbYY6rAL0kzeKjQP | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/Gen4KAk6gqXYddjH0D5Rm7vL2aDmOPEQ | Click me | Not Sent | door to the property | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18141131867%20-%20141%20%20B%20East%20Walnut%20Street&text_mkw2a9my=18141131867&text_mkw2sbhy=141%20%20B%20East%20Walnut%20Street | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18141131867%20-%20141%20%20B%20East%20Walnut%20Street&text_mkw2a9my=18141131867&text_mkw2sbhy=141%20%20B%20East%20Walnut%20Street | 141 B East Walnut Street, 141 B East Walnut Street, 141 B East Walnut Street, 141 B East Walnut Street, 141 B East Walnut Street, 141 B East Walnut Street, 141 B East Walnut Street | Not Done | 2025-11-21 | 141 B East Walnut Street | 4.63, 2.23, 1.13, 2.05, 2.93, 2.83, 2.72, 2.5, 4.05, 2.62, 1.33, 2.25 | 18141132619 | 141 East Walnut Street Apt B Oglesby IL 61348 | C & R Property Solutions- 141-149 E Walnut Series | hablair80@gmail.com | 3 | 2 | 0 | hablair80@gmail.com | Approved | Waiting on Approval | Picture in Rentvine | Build Estimate | Build Change Order | Change Order Created: This change order adds four hours of labor to complete exterior cleanup around the unit. Material cost: $0 Labor cost: $260 Total cost: $260 --------------------------------------------------------------------------------------------------------------------------- 141 B East Walnut Street will undergo a full cosmetic and functional refresh. Painting and drywall repairs include patching small holes, repainting doors, baseboards, shelving, and high‐heat baseboard heaters, as well as refinishing trim and doorjambs. Cleaning tasks cover sticker removal, outlet cleaning, and general debris removal. Electrical work replaces dim or burned‐out bulbs in fixtures and ceiling fans throughout the unit. Additional scope covers minor carpentry and miscellaneous labor: replacing damaged trim and corner pieces, disassembling and removing furniture, replacing air filters, and light lawn care behind the deck. All sourced materials (molding, bulbs, control rods, ceiling tiles, drywall, furnace filter) are procured to complete these tasks and ensure the unit is move‐in ready. Costs Material Cost: $84.05 Labor Cost: $1,070.65 Total Estimated Cost: $1,154.70 Materials (qty, unit price, total): • Cove molding (4 ea @ $9.20): $36.80 • Bulbs (1 ea @ $12.50): $12.50 • Blind control rod (1 ea @ $7.80): $7.80 • Ceiling tile (1 ea @ $6.80): $6.80 • 2×2 drywall (1 ea @ $12.00): $12.00 • Furnace filter (1 ea @ $8.15): $8.15 Tenant‐billed amounts (credited against owner costs): Tenant‐billed Labor: $261.30 Tenant‐billed Materials: $20.65 | Send Estimate to Owner |  |  | 2025-11-10 | Send CO Email | This change order adds four hours of labor to complete exterior cleanup around the unit. Material cost: $0 Labor cost: $260 Total cost: $260 Specific materials: None. | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | - Source cove molding: 4 ea - Source bulbs: 1 ea - Source control rods for blinds: 1 ea | - 2x2 drywall: 1 ea | - Ceiling tile – 1 ea - Furnace filter – 1 ea |  | Cost Calculator | Calculated | Calculated | Third Party | 1070.65 | 84.05 | 1154.7 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=18141131867&decision=approved | Approve CO ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=18141131867&decision=approved | Yes | 1300 | 261.3 | 20.65 |  |  | 141 B East Walnut Street |  |  |  | 18141131867
1339 Kansas B Ottawa |  |  |  | 2025-09-16 |  | Erica Mukes |  |  |  |  | 2025-09-18 | [10 empty] | 0 |  | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/1ac4cf7aaaf84c48a5c1735a90089d7b | Send Email | 2025-09-18 | 2025-11-25 | 2025-11-26 | 10007475- codebox max |  | v |  |  | 850 | New Pictures In Rentvine | Ready To Market | Deposit Received | Duplex |  | Overdue | Yes | Add | Full Service | 1339 Kansas Street Apt B Ottawa IL 61350, 1339 Kansas Street Apt B Ottawa IL 61350, 1339 Kansas Street Apt B Ottawa IL 61350 | Completed, Completed, Completed | 1.47, 7.87, 1.3, 4.58, 8.03, 1.0, 2.58, 7.0, 3.08, 0.67, 4.08, 1.6, 4.28, 8.0, 2.28, 5.38, 6.5, 6.83, 7.25 | 894, 390 | 1046, 490, 0 | 0, 00 | 5 |  | 2025-11-25 | 2026-01-20 | 85.7286 | 55 | Sep 12, 2025 10:23 AM | Thalia |  | 154.7286 |  | 4383.9765 |  | 68 | 10039365075 | 1 | 2 | 2025-09-19 | 2025-11-25 |  | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/oPkwzjdVyq7mQQdIzzY3Q7Dl8pQLYA3e | Click me | Not Sent | front door | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=10039365075%20-%201339%20Kansas%20B%20Ottawa&text_mkw2a9my=10039365075&text_mkw2sbhy=1339%20Kansas%20B%20Ottawa |  | 1339 Kansas B, 1339 Kansas B, 1339 Kansas B, 1339 Kansas B, 1339 Kansas B | Not Done | 2025-11-21, 2025-10-17, 2025-10-17, 2025-10-31, 2025-11-05 | 1339 Kansas B, 1339 Kansas B | 4.28, 1.47, 7.87, 5.38, 1.6, 6.5, 6.83, 7.25, 8.0, 1.3, 2.28, 4.58, 1.0, 8.03, 2.58, 7.0, 3.08, 0.67, 4.08, 4.58, 1.0, 8.03, 2.58, 7.0, 3.08, 0.67, 4.08 | 18085588776, 18233480739 | [8 empty] | Ready to Send | Picture in Rentvine | Build Estimate | Build Change Order |  | Send Estimate to Owner |  |  |  | Send CO Email | Change Order at 1339 Kansas B to remove damaged subfloor, install new subflooring and complete finish flooring work. This covers 5 hours of labor for subfloor removal, installation and surface finishing, plus purchase of replacement subfloor material. Material cost: $35.00 Labor cost: $250.00 Total cost: $285.00 Materials: - Replacement subflooring: $35.00 | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com |  | Build Material List | [5 empty] | Cost Calculator | Calculated | Calculated | KPON |  |  | 0 |  | Approve CO ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=10039365075&decision=approved | No | 850 | 0 | 0 |  |  | 1339 Kansas B |  |  |  | 10039365075
424 Heritage East Ottawa |  |  |  | 2025-10-30 |  | Ethan Bernath, Dominique Helena Franz |  |  |  |  | 2025-10-29 | [12 empty] | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/9dcbd0e997164c51a0a97cc200e512b1 | Send Email | 2025-10-30 | 2026-01-09 | 2026-01-12 | 2294474-sentrilock |  |  |  |  | 1300 | Previous Photos Good | Ready To Market | Deposit Received | Duplex |  | Overdue | Yes | Add | Full Service | 424 Heritage EastTO/Tenant Billed, 424 Heritage EastTO/General Maintenance, 424 Heritage EastTO/Painting, 424 Heritage E/TO/Final Maintenance | Completed, Completed, Completed, Completed | 1.2, 4.0, 3.42, 0.77, 1.83, 1.83, 1.5, 1.37, 0.73, 5.32, 1.97, 1.75, 0.68, 2.68, 1.7, 1.27, 0.83, 2.18, 4.98, 2.62, 4.6, 2.82, 2.53 | 1040, 430, 350 | 620, 0, 0, 215 | 0, 000, 00 | 23.246 | 232.0829 | 2026-01-09 | 2026-01-20 | 38.7286 | 8 | Oct 30, 2025 11:36 AM | Thalia |  | 113.7286 |  | 4928.2386 |  | 71 | 18310977798 | 1 | 1 | 2025-11-03 | 2026-01-02 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/2VMLonxWde7zwwWUwxqRGXR8lgN6GpAm | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/y3R1odap8qX0xxZFy6NZVXNMegBx0YzG | Click me | Not Sent | front door of the property | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18310977798%20-%20424%20Heritage%20East%20Ottawa&text_mkw2a9my=18310977798&text_mkw2sbhy=424%20Heritage%20East%20Ottawa | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18310977798%20-%20424%20Heritage%20East&text_mkw2a9my=18310977798&text_mkw2sbhy=424%20Heritage%20East | 424 Heritage East, 424 Heritage East, 424 Heritage East, 424 Heritage East, 424 Heritage East, 424 Heritage East, 424 Heritage East, 424 Heritage East | Not Done | 2025-11-21, 2025-11-21 | 424 Heritage East | 1.2, 4.0, 3.42, 1.83, 0.77, 1.83, 1.5, 0.73, 5.32, 2.68, 1.7, 1.97, 1.37, 1.27, 2.18, 0.68, 1.75, 0.83, 4.98, 2.62, 1.37, 4.6, 2.82, 2.53 | 18310978570 | [6 empty] | keith@kponproperties.com | Approved | Approved | Picture in Rentvine | Build Estimate | Build Change Order | Change Order Created: This change order provides six additional hours of labor to remove remaining tenant belongings from the unit at 424 Heritage East, ensuring the space is fully cleared and ready for turnover. Material Cost: $0 Labor Cost: $390 Total Estimated Cost: $390 Materials: • None (no materials required) ------------------------------------------------------------------------------------------------------- Turnover at 424 Heritage East includes full unit clean-up, minor repairs, and component replacements to restore functionality and appearance. Crews will remove all abandoned items, clean light fixtures, smoke detectors, walls and door casings, and clear the garage (leaving specified equipment). Extensive painting covers baseboards, doors, door casings and sliding-door frames throughout living areas, bedrooms, hallway, kitchen and bathroom. Patching and drywall work includes repairing holes and scratches in walls and ceilings, installing a half-sheet of drywall in the garage, redoing ceiling patches, and recaulking around the bathtub. Hardware adjustments and general maintenance address plumbing under the kitchen sink and secure loose bracket and door-casing fasteners. Appliance and fixture replacements consist of new living-room blinds, a new wall-mounted AC unit due to age and functionality, and a replacement window screen in the left bedroom. These updates ensure the unit meets move-in standards. Costs • Material cost: $454.09 • Labor cost: $1,050.57 • Total estimated cost: $1,504.66 Materials detail • 37×54" blinds: $41.59 • 19×14" wall AC unit: $406.00 • Drywall sheet (28¾"×47½", 0.5 qty): $6.50 | Send Estimate to Owner |  |  | 2025-11-05 | Send CO Email | This change order provides six additional hours of labor to remove remaining tenant belongings from the unit at 424 Heritage East, ensuring the space is fully cleared and ready for turnover. Material Cost: $0 Labor Cost: $390 Total Estimated Cost: $390 Materials: • None (no materials required) | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | - Source 37×54 blinds – 1 ea - Source 19×14 wall AC unit – 1 ea | None | - 0.5 sheet Drywall/Plaster (28.75 in x 47.5 in) |  | Cost Calculator | Calculated | Calculated | KPON | 1050.565 | 454.09 | 1504.655 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=18310977798&decision=approved | Approve CO ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=18310977798&decision=approved | Yes | 1300 | 761.875 | 41.59 |  |  | 424 Heritage East, 424 Heritage East, 424 Heritage East Ottawa | 2025-11-21 |  |  | 18310977798
2018 First Street Peru IL 61354 |  |  |  | 2025-10-31 | 2026-02-02 | Tonya Fry |  |  |  |  | 2025-11-30 |  |  |  | 1715 8th St | New place | [7 empty] | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/21f77e25d4144902996e77b3fe4e3c90 | Send Email | 2025-11-28 | 2026-01-15 | 2026-01-16 | 2301405 Sentrilock |  | v |  |  | 1100 | New Pictures In Rentvine | Ready To Market | Deposit Received | Duplex |  | Overdue | Yes | Add | Full Service | 2018 First Street Peru IL 61354TO/Tenant Billed, 2018 First Street Peru IL 61354TO/General Maintenance, 2018 First Street Peru IL 61354TO/Painting, 2018 First Street Peru IL 61354 | Completed, Completed, Completed, Reschedule | 4.17, 3.42, 3.08, 3.75, 0.75, 0.33, 1.33, 3.42, 1.67, 1.92, 4.83, 2.83 | 1045.55 | 0, 138, 0, 0 | 0 | 22.03 | 146.3913 | 2026-01-15 | 2026-01-26 | 34.7286 | 10 | Oct 31, 2025 6:14 PM | Thalia | 64 |  | 2346.6667 |  |  | 48 | 18322976941 | 1 | 1 | 2025-12-04 | 2026-01-09 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/k3pvoQ4ae6XWBBEFoozPz7DqO9NxnWlK | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/dyYW2jB9wVr5qqBfb1QGzrlq45zkRO1P | Click me | Not Sent | Front door | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18322976941%20-%202018%20First%20Street%20Peru%20IL%2061354&text_mkw2a9my=18322976941&text_mkw2sbhy=2018%20First%20Street%20Peru%20IL%2061354 | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18322976941%20-%202018%20First%20Street%20Peru%20IL%2061354&text_mkw2a9my=18322976941&text_mkw2sbhy=2018%20First%20Street%20Peru%20IL%2061354 | 2018 First Street Peru IL 61354, 2018 First Street Peru IL 61354, 2018 First Street Peru IL 61354, 2018 First Street Peru IL 61354, 2018 First Street Peru IL 61354 | Not Done |  | 2018 First Street Peru IL 61354 | 3.08, 0.75, 0.33, 1.33, 0.75, 3.42, 1.67, 1.92, 4.83, 4.17, 3.42, 3.75, 2.83 | 18322977096 | 2018 First Street Peru IL 61354 | C & R Property Solutions LLC- 2016-2018 First Street Series | johnnyb@fullcircleindustrial.com | 3 | 1 | 0 | johnnyb@fullcircleindustrial.com | Approved | Approved | Picture in Rentvine | Build Estimate | Build Change Order | 2018 First Street will receive a full cleaning and minor repairs to restore functionality and appearance. Exhaust fans and light fixtures will be cleaned, loose hardware (showerhead trim, toilet paper holder) tightened, and debris removed throughout, including a sweep of the basement floor. A new drain pipe will be installed on the HVAC condensation line to prevent water damage. Electrical work includes replacing all burnt-out interior and exterior bulbs for consistent lighting. Cosmetic updates feature a full bathroom repaint (walls, baseboards, door) plus targeted touch-ups in bedrooms, living areas, and the kitchen—refreshing walls, window sills, door frames, and baseboards to ensure a uniform, move-in-ready finish. Material cost: $138.00 Labor cost: $1,045.55 Total cost: $1,183.55 Materials: - Sherwin paint (3 gallons): $114.00 - HVAC condensation drain pipe: $16.00 - Replacement light bulbs (4-pack): $8.00 Tenant-billed amounts (reduces owner’s portion): - Labor: $57.50 - Materials: $8.00 | Send Estimate to Owner |  |  | 2025-12-11 | Send CO Email |  | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | None | - 1 ea: 4 bulbs for burnt out replacement | - Source paint: 3 gallon - HVAC condensation line: 1 ea |  | Cost Calculator | Calculated | Calculated | Third Party | 1045.55 | 138 | 1183.55 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=18322976941&decision=approved | CO Manual Approval ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=18322976941&decision=approved | Yes | 1100 | 57.5 | 8 |  |  | 2018 First Street Peru IL 61354 | 2025-12-15 | Standard |  | 18322976941
600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy) |  |  |  | 2025-08-28 | 2026-01-30 | Zachary Gerling | gerlingzachary@gmail.com |  |  | 18156835006 | 2025-10-30 |  |  |  | 379 E State Route 54 Onarga, IL | Relocating for a new job | https://tcg356580.monday.com/protected_static/14862391/resources/2524940271/image.jpg | https://tcg356580.monday.com/protected_static/14862391/resources/2524940387/image.jpg | https://tcg356580.monday.com/protected_static/14862391/resources/2524940493/image.jpg | https://tcg356580.monday.com/protected_static/14862391/resources/2524940584/image.jpg |  | 1 |  | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/55c56aedf556447ab0ff62de7631afdd | Send Email | 2025-10-30 | 2026-01-12 | 2026-01-12 | 20010094 mini codebox |  |  |  |  | 900 | New Pictures In Rentvine | Ready To Market | Deposit Received | Apartment |  | Overdue | No | Add | Full Service | 600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy)TO/General Maintenance, 600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy)TO/Painting | Completed, Completed | 0.27, 3.12, 2.08, 4.82 | 525, 65 | 78, 15 | 0, 0 | 8.44 | 121.9194 | 2026-01-12 | 2026-01-26 | 38.7286 | 14 | Oct 31, 2025 1:40 PM | Thalia | 92 |  | 2760 |  |  | 74 | 18321320734 | 1 |  | 2025-10-31 |  | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/jNlAe54bq17MwwMUZqydgrpk3aEWoxZY | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/n18pexyNQjJ4qqNfWxB1D7Eq96bw4WDR | Click me | Not Sent | back of the building railing | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18321320734%20-%20600%20E%20McKinley%20Rd.%20Apt%203A%20Ottawa,%20IL%2061350%20(copy)&text_mkw2a9my=18321320734&text_mkw2sbhy=600%20E%20McKinley%20Rd.%20Apt%203A%20Ottawa,%20IL%2061350%20(copy) | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18321320734%20-%20600%20E%20McKinley%20Rd.%20Apt%203A%20Ottawa%2C%20IL%2061350%20(copy)&text_mkw2a9my=18321320734&text_mkw2sbhy=600%20E%20McKinley%20Rd.%20Apt%203A%20Ottawa%2C%20IL%2061350%20(copy) | 600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy), 600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy), 600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy), 600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy), 600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy), 600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy), 600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy), 600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy), 600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy) | Not Done | 2025-11-21, 2025-11-21 | 600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy) | 0.27, 3.12, 4.82, 2.08 | 18321321855 | 600 E Mckinley Road Apt 3A Ottawa IL 61350 | Hope Investments, LLC | jnord107@aol.com | 2 | 1 | 0 | jnord107@aol.com | Approved | Approved | Picture in Rentvine | Build Estimate | Build Change Order | Property: 600 E McKinley Rd. Apt 3A, Ottawa, IL 61350 Change Order Created: Change Order for 600 E McKinley Rd. Apt 3A, Ottawa, IL 61350: Adds five additional labor hours of painting to complete final trim and wall finishes as required for turnover. Material cost: $0 Labor cost: $175 Total cost: $175 Specific materials: None ----------------------------------------------------------------------------------------------------------------- This turnover scope includes general cleaning and light fixture maintenance (entry door wipe-down, light globe cleaning), HVAC servicing (vent cleaning, filter replacement), and a plumbing repair (sink sprayer replacement). Carpets will be evaluated for repair near the bathroom. Drywall and plaster work consists of patching nail holes and touch-ups in the living room. The painting package covers baseboard repainting in the living room, dining room, and back bedroom, plus full-surface touch-up on an east wall cut-out. Two paint colors will be sourced—Sherwin trim paint and light French gray—to ensure a uniform finish and restore the unit to market-ready condition. Cost Summary • Labor: $128.10 • Materials: $140.00 • Total Estimated Cost: $268.10 Materials Detail • Sherwin trim paint (1 gal): $35.00 • Sherwin light French gray paint (1 gal): $50.00 • Furnace filter (1 ea): $22.00 • Sink sprayer (1 ea): $33.00 | Send Estimate to Owner |  |  |  | Send CO Email | Change Order for 600 E McKinley Rd. Apt 3A, Ottawa, IL 61350: Adds five additional labor hours of painting to complete final trim and wall finishes as required for turnover. Material cost: $0 Labor cost: $175 Total cost: $175 Specific materials: None | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | - Furnace filter, 1 ea - Sink sprayer, 1 ea | None | - Source trim paint: 1 gallon - Source light French gray: 1 gallon |  | Cost Calculator | Calculated | Calculated | Nordstrom | 128.1 | 140 | 268.1 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=18321320734&decision=approved | Approve CO ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=18321320734&decision=approved | Yes | 900 | 0 | 0 |  |  | 600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy), 600 E McKinley Rd. Apt 3A Ottawa, IL 61350 (copy) |  |  |  | 18321320734
1444 State, #8, Ottawa |  |  |  | 2025-10-12 |  | Amanda Sedlak, William Sedlak | amandasedlak@yahoo.com | wjsedlak@yahoo.com |  | 12242795709 | 2025-11-05 |  |  |  | 628 W. Peregrine Dr, Palatine, IL 60067 | New Job in Crystal Lake IL | [5 empty] | 5 |  | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/1e5d0bb5abcf4cde947f3811b0598937 | Send Email | 2025-11-05 | 2026-01-09 | [6 empty] | 1600 | New Pictures In Rentvine | Ready To Market | Deposit Received | Furnished - Medium Term |  | Overdue | Yes | Add |  | 1444 State, #8, OttawaTO/Tenant Billed, 1444 State, #8, OttawaTO/General Maintenance, 1444 State, #8, OttawaTO/Painting | Completed, Completed, Completed | 0.17, 0.83, 1.17, 2.42 |  | 0, 0, 0 |  | 7 |  | 2026-01-09 | 2026-01-27 |  |  | Oct 12, 2025 11:30 AM | Thalia |  | 106.7286 |  | 5692.1911 |  | 65 | 18166324551 | 1 | 2 | 2025-11-11 | 2026-01-09 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/9BZeb6q2RV7NYY9HddQOZJ1MgvN3EDGO | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/j4oWg1RQMArKPP9F5YBA0JlEOa23kpqP | Click me | Not Sent |  | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18166324551%20-%201444%20State,%20#8,%20Ottawa&text_mkw2a9my=18166324551&text_mkw2sbhy=1444%20State,%20#8,%20Ottawa | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18166324551%20-%201444%20State%2C%20%238%2C%20Ottawa&text_mkw2a9my=18166324551&text_mkw2sbhy=1444%20State%2C%20%238%2C%20Ottawa | 1444 State, #8, Ottawa, 1444 State, #8, Ottawa, 1444 State, #8, Ottawa, 1444 State, #8, Ottawa, 1444 State, #8, Ottawa, 1444 State, #8, Ottawa, 1444 State, #8, Ottawa | Not Done |  | 1444 State Street, #8, Ottawa, 1444 State, #8, Ottawa | 0.83, 0.17, 2.42, 1.17, 0.83, 0.17, 2.42, 1.17 | 18154730845, 18166324658 | [7 empty] | Approved |  | Picture in Rentvine | Build Estimate | Build Change Order | At 1444 State #8 we will perform targeted cosmetic and functional repairs to return the unit to rentable condition. This includes paint touch-ups in the living and dining rooms, drywall patching in the bedroom, and re-caulking in the bathroom. We’ll also replace the rusty bathroom vent cover and ensure all plumbing fixtures are sealed properly. In addition, minor electrical work (light bulbs and a kitchen fixture) and removal of personal items from the kitchen are scheduled. Materials for vent covering and bulbs are supplied, and cleaning/prep labor for clearing counters and the refrigerator will be charged back to the outgoing tenant. Material cost: $56 Labor cost: $257 Total cost: $313 Specific materials: - Bathroom vent cover: $8 - Light bulbs (4 ea): $48 Tenant-billed amounts (reduces owner’s portion): - Tenant-billed labor: $47 - Tenant-billed materials: $48 | Send Estimate to Owner |  |  |  | Send CO Email |  | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | - Replace bathroom vent cover: 1 hours | - Light bulbs: 4 ea | None |  | Cost Calculator | Calculated | Calculated | Nordstrom | 257 | 56 | 313 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=18166324551&decision=approved | CO Manual Approval ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=18166324551&decision=approved | Yes | 1600 | 47 | 48 | [6 empty] | 18166324551
2406 Marquette Road Apt 5 Peru IL 61354 |  |  |  | 2025-10-21 | 2026-01-27 | Dionne Borden, Bryan James Kahler |  |  |  |  | 2025-11-30 | v | v | v | PO Box 1134, LaSalle IL 61301 | Temp living | [7 empty] | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/e3551cc22ed64fbca8b9221a16bed8e3 | Send Email | 2025-12-05 | 2026-01-14 | 2026-01-15 | 10100646 |  |  |  |  | 825 | New Pictures In Rentvine | Ready To Market | Deposit Received | Apartment |  | Overdue | Yes | Add | Full Service | 2406 Marquette Rd unit 1-6 building, 2406 Marquette Road Apt 5 Peru IL 61354TO/Painting, 2406 Marquette Road Apt 5 Peru IL 61354TO/General Maintenance | Completed, Completed, Tech Closed | 1.17, 1.42, 3.78 | 58.75, 207.5 | 0, 0, 82 | 000, 0 | 12 | 58.1667 | 2026-01-14 | 2026-01-27 | 35.729 | 12 | Oct 21, 2025 11:01 AM | Thalia | 58 |  | 1595 |  |  | 40 | 18235173568 | 1 | 2 | 2025-12-05 | 2026-01-12 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/mAe53PLn4vrDvv1Fjj9DZ7EKM9Zoj0Bp | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/aLBOjwoQAVrAzzMulaojjJyNDWRnK8Y2 | Click me | Not Sent | unit door | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18235173568%20-%202406%20Marquette%20Road%20Apt%205%20Peru%20IL%2061354&text_mkw2a9my=18235173568&text_mkw2sbhy=2406%20Marquette%20Road%20Apt%205%20Peru%20IL%2061354 | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18235173568%20-%202406%20Marquette%20Road%20Apt%205%20Peru%20IL%2061354&text_mkw2a9my=18235173568&text_mkw2sbhy=2406%20Marquette%20Road%20Apt%205%20Peru%20IL%2061354 | 2406 Marquette Road Apt 5 Peru IL 61354, 2406 Marquette Road Apt 5 Peru IL 61354, 2406 Marquette Road Apt 5 Peru IL 61354, 2406 Marquette Road Apt 5 Peru IL 61354, 2406 Marquette Road Apt 5 Peru IL 61354 | Not Done |  | 2406 Marquette Road Apt 5 Peru IL 61354 | 3.78, 1.42, 1.78 | 18235174526 | 2406 Marquette Road Apt 5 Peru IL 61354 | Hope Investments, LLC - Oak Terrace Series | jnord107@aol.com | 1 | 1 | 0 | jnord107@aol.com | Approved |  | Picture in Rentvine | Build Estimate | Build Change Order | This turnover will address sealing and trim repairs in the bathroom (securing vinyl baseboard and re‐caulking behind the sink), correct a minor kitchen plumbing issue at the sink, and refresh paint and clean overspray in the bedroom and living room (touch-ups on walls, doors, vents, and baseboards). Window and patio door functionality will be restored by removing the magnetic screen, scraping sticker residue, installing a new blind track above the patio door, and supplying a new vertical blind rail. Finally, hall-closet shelving will be replaced with a new white shelf unit and all necessary caulk and paint supplies provided. These improvements ensure the unit is clean, watertight, and fully functional, with fresh finishes throughout and working window treatments. They bring the property back to move-in standards and prevent future tenant complaints or maintenance calls. Material Cost: $129.50 Labor Cost: $595.00 Total Estimated Cost: $724.50 Specific Materials - Hall-closet white shelving (Menards): $13.50 - New vertical blind rail (Menards): $66.00 - Caulk and paint supplies (Route 6 Shop): $50.00 Tenant-Billed Labor: $0.00 Tenant-Billed Material: $0.00 | Send Estimate to Owner |  |  |  | Send CO Email |  | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | - 1 ea Source white shelving to replace hall closet shelves - 1 ea New vertical blind rail | - Caulk/Paint supplies: 1 ea | None |  | Cost Calculator | Calculated | Calculated | Nordstrom | 595 | 129.5 | 724.5 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=18235173568&decision=approved | CO Manual Approval ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=18235173568&decision=approved | Yes | 825 | 0 | 0 |  |  | 2406 Marquette Road Apt 5 Peru IL 61354 | 2025-12-15 | Light |  | 18235173568
445 Elm Place R-13 Princeton IL 61356 |  |  |  | 2025-10-31 | 2026-02-08 | Reyne Dockins |  |  |  |  | 2025-11-10 |  |  |  | R-12 Elm | Management SUCKS :P | [5 empty] | 5 | But Nathan was great | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/637d174f030c4da680b58db4bfb8677d | Send Email | 2025-11-11 | 2026-01-14 | 2026-01-15 | 2252001-sentrilock |  |  |  |  | 825 | New Pictures In Rentvine | Ready To Market | Deposit Received | Apartment |  | Overdue | Yes | Add | Full Service | 445 Elm Place R-13 Princeton IL 61356TO/Tenant Billed, 445 Elm Place R-13 Princeton IL 61356TO/General Maintenance, 445 Elm Place R-13, R13/TO/Final Maintenance | Cancelled, Completed, Completed, Completed | 0.08, 2.98, 4.42, 3.08, 3.83, 4.67, 2.83, 4.42, 2.75, 2.92, 3.83, 2.75, 5.33, 1.88, 3.5, 3.67, 3.17, 3.33, 4.0, 1, 4, 2.58, 3.58, 3.92, 3.67, 4.5, 0.92 | 3176.25 | 0, 397, 0, 0 | 0 | 61 | 122.0328 | 2026-01-14 | 2026-01-28 | 35.729 | 13 | Oct 31, 2025 1:18 PM | Thalia | 90 |  | 2475 |  |  | 64 | 18321091237 | 1 | 1 | 2025-11-20 | 2026-01-02 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/lkAKgaRjv97EQQAI442je7e86yEMzp23 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/vBaR8ePW69rvppZfZGjGK73dpzyZj41Y | Click me | Not Sent | unit door | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18321091237%20-%20445%20Elm%20Place%20R-13%20Princeton%20IL%2061356&text_mkw2a9my=18321091237&text_mkw2sbhy=445%20Elm%20Place%20R-13%20Princeton%20IL%2061356 | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18321091237%20-%20445%20Elm%20Place%20R-13%20Princeton%20IL%2061356&text_mkw2a9my=18321091237&text_mkw2sbhy=445%20Elm%20Place%20R-13%20Princeton%20IL%2061356 | 445 Elm Place R-13 Princeton IL 61356, 445 Elm Place R-13 Princeton IL 61356, 445 Elm Place R-13 Princeton IL 61356, 445 Elm Place R-13 Princeton IL 61356, 445 Elm Place R-13 Princeton IL 61356, 445 Elm Place R-13 Princeton IL 61356 | Not Done |  | 445 Elm Place R-13 Princeton IL 61356 | 3.08, 2.98, 3.83, 4.67, 4.42, 2.75, 2.83, 4.42, 3.83, 2.92, 5.33, 1.88, 2.75, 3.17, 3.67, 3.5, 3.33, 4.0, 0.08, 1, 6, 4 | 18321091586 | 445 Elm Place R-13 Princeton IL 61356 | Andrea C Nordstrom, Gentry Nordstrom, Hope Investments, LLC - Elm Place Series | andrea.nordstrom@gmail.com; andrea.nordstrom@gmail.com; gentry.nordstrom@gmail.com | 2 | 1 | 0 | gentry@thechrysalis.group | Approved |  | Not Done | Build Estimate | Build Change Order | The scope of this turnover covers three main work types. Electrical upgrades include replacing all yellowed outlets and switches, installing new lightbulbs in the exhaust fan and left‐bedroom closet, replacing the oven clock button and pull-string, and performing miscellaneous fixture tightening (refrigerator handle, sprayer base, and light-fixture cleaning). Plumbing tasks address minor leaks and securements—repairing a leaking shower wand and trim ring, installing a new discharge pipe on the water heater, tightening the kitchen sprayer, and re-caulking surrounds. Surfaces and hardware receive a full refresh. A new 36″ bathroom vanity and medicine cabinet are installed, quarter-round trim is added throughout, and one section of baseboard and two baseboard heaters are replaced. Cabinet pulls are updated in the kitchen, control rods in a bedroom blind are swapped out, and back-bedroom closet door hardware and knobs are renewed. Finally, closets and entry doors are aligned, hooks and wrapping paper removed, and all interior painting (including hallway-closet shelves) is quoted, restoring clean, uniform finishes. Material Cost: $680.30 Labor Cost: $3,324.83 Total Estimated Cost: $4,005.13 Specific Materials • 20 ea. electrical outlets @ $1.41 ea. = $28.20 • 20 ea. light switches @ $1.13 ea. = $22.60 • 1 ea. 36″ bathroom vanity = $257.00 • 25 ea. kitchen cabinet pulls @ $2.10 ea. = $52.50 • 1 ea. 28″ bathroom baseboard heater = $46.00 • 1 ea. 250′ quarter round = $115.00 • 1 ea. 3′ baseboard section = $11.00 • 1 ea. blind control rod = $4.00 • 2 ea. back-bedroom door knobs @ $2.50 ea. = $5.00 • 1 ea. bedroom blind pull-string = $5.00 • 1 ea. medicine cabinet = $110.00 • 1 ea. oven clock button = $22.00 • 1 ea. exhaust-fan bulb = $2.00 Tenant-Billed Portions • Tenant-billed Labor: $65.00 • Tenant-billed Materials: $32.00 | Send Estimate to Owner |  |  | 2025-11-24 | Send CO Email |  | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | - Outlets - yellowed- replace: 20 ea - Switches - yellowed- replace: 20 ea - Bathroom vanity - 36 inch: 1 ea - Pulls - kitchen cabinet: 25 ea - Replace bathroom baseboard heater - 28 inch: 1 ea - Replace control rod in middle blind in left bedroom: 1 ea - Replace door knobs in back bedroom on the closet: 2 ea - Replace pull string in left bedroom: 1 ea - 250' Quarter Round: 1 ea - Medicine cabinet: 1 ea | • Bulb, bathroom exhaust fan – 1 ea | - Replace section of baseboard – 3 foot in left bedroom behind bedroom door: 1 ft - Button for oven clock: 1 ea | 445 Elm Place R-13 Princeton IL 61356 | Cost Calculator | Calculated | Calculated | Nordstrom | 3324.825 | 680.3 | 4005.125 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=18321091237&decision=approved | CO Manual Approval ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=18321091237&decision=approved | Yes | 825 | 65 | 32 |  |  | 445 Elm Place R-13 Princeton IL 61356 | 2025-12-08 | Heavy |  | 18321091237
2406 Marquette Road Apt 12 Peru IL 61354 |  |  |  | 2025-10-26 | 2026-02-10 | Christina M Fuentes, Matthew Thomas Mikyska |  |  |  |  | 2025-10-31 |  |  |  | 1513 Green St Peru, Illinois 61354 | Bought a house | [7 empty] | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/7a35185feac64132a266a032d8398b3c | Send Email | 2025-10-31 | 2026-01-19 | 2026-01-19 | 10011917 codebox |  |  |  | v | 825 | New Pictures In Rentvine | Ready To Market | Deposit Received |  |  |  | Yes | Add | Full Service | 2406 Marquette Road Apt 12 Peru IL 61354TO/Painting, 2406 Marquette Road Apt 12 Peru IL 61354TO/Tenant Billed, 2406 Marquette Road Apt 12 Peru IL 61354TO/General Maintenance, 2406 Marquette Rd Unit 12 | Completed, Completed, Completed, Completed | 5.07, 1.58, 5.35, 1.13 | 260, 350, 58.75 | 0, 55, 108.9, 12.81 | 00, 0000, 00 | 12.999 | 112.7779 | 2026-01-19 | 2026-02-02 | 31.729 | 14 | Oct 26, 2025 8:47 PM | Thalia | 102 |  | 2805 |  |  | 80 | 18273256985 | 1 | 1 | 2025-11-04 | 2026-01-07 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/pqxEkdlgY1JVVVWiA4P0OJZwPDbLWem3 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/05B3zlY9GoJ9RRQFM0woK7Egemkb28v6 | Click me | Not Sent | unit door | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18273256985%20-%202406%20Marquette%20Road%20Apt%2012%20Peru%20IL%2061354&text_mkw2a9my=18273256985&text_mkw2sbhy=2406%20Marquette%20Road%20Apt%2012%20Peru%20IL%2061354 | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18273256985%20-%202406%20Marquette%20Road%20Apt%2012%20Peru%20IL%2061354&text_mkw2a9my=18273256985&text_mkw2sbhy=2406%20Marquette%20Road%20Apt%2012%20Peru%20IL%2061354 | 2406 Marquette Road Apt 12 Peru IL 61354, 2406 Marquette Road Apt 12 Peru IL 61354, 2406 Marquette Road Apt 12 Peru IL 61354, 2406 Marquette Road Apt 12 Peru IL 61354, 2406 Marquette Road Apt 12 Peru IL 61354, 2406 Marquette Road Apt 12 Peru IL 61354, 2406 Marquette Road Apt 12 Peru IL 61354, 2406 Marquette Road Apt 12 Peru IL 61354 | Not Done | 2025-11-21 | 2406 Marquette Road Apt 12 Peru IL 61354 | 1.58, 5.35, 5.07, 1.13, 1.13, .4 | 18273257260 | 2406 Marquette Road Apt 12 Peru IL 61354 | Hope Investments, LLC - Oak Terrace Series | jnord107@aol.com | 1 | 1 | 0 | jnord107@aol.com | Approved |  | Not Done | Build Estimate | Build Change Order | 2406 Marquette Road Apt 12, Peru IL 61354 will receive a full cosmetic refresh and basic maintenance to ensure all fixtures and finishes are in working order. Painting includes patching and repainting walls, doors, baseboards and closets in the hallway, kitchen, living room, bathroom and bedroom closet. Plumbing work covers recaulk of the tub and sink surrounds, replacement of the showerhead and faucet assembly, and installation of a new toilet seat. Appliance upkeep consists of swapping out the oven drip pans, and safety checks include replacing the smoke‐detector battery. These updates restore the unit’s appearance, address water‐tightness in wet areas, and maintain essential safety and appliance functions ahead of new occupancy. Material cost: $163.70 Labor cost: $379.94 Total estimated cost: $543.64 Materials • Showerhead faucet assembly: $108.00 • Toilet seat: $16.20 • Oven drip pans: $14.50 • Paint (1 gallon): $25.00 Amounts billed back to tenant • Tenant‐billed labor: $64.94 • Tenant‐billed materials: $30.70 | Send Estimate to Owner |  |  |  | Send CO Email |  | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | • Toilet seat: 1 ea • Drip pans: 1 ea | - Paint: 1.0 gallon | - Showerhead faucet: 1 ea |  | Cost Calculator | Calculated | Calculated | Nordstrom | 379.935 | 163.7 | 543.635 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=18273256985&decision=approved | CO Manual Approval ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=18273256985&decision=approved | Yes | 825 | 64.935 | 30.7 |  |  | 2406 Marquette Road Apt 12 Peru IL 61354 | 2025-11-10 | Light |  | 18273256985
1101 Carrie Lane Apt. 7 Marseilles IL 61341 |  |  |  | 2025-12-12 | 2026-02-23 | Christopher Pelletier |  |  |  |  | 2026-01-01 |  |  |  | 9 Merrill Ave Unit 4 | Family emergency out of state | [7 empty] | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/20420d475023464dbfdc62c8347d4555 | Send Email | 2026-01-12 | 2026-02-05 | 2026-02-05 |  |  |  |  | v | 800 |  | Ready To Market | Deposit Received | Apartment |  |  | Yes | Add | Full Service | 1101 Carrie Lane Apt. 7 Marseilles IL 61341TO/General Maintenance, 1101 Carrie Lane Apt. 7 Marseilles IL 61341TO/Painting | Completed, Completed | 0.72, 2.0, 0.55, 3.08 | 257.5 | 62.76, 0 | 0 | 5 | 127 | 2026-02-05 | 2026-02-09 | 14.729 | 4 | Dec 12, 2025 1:07 PM | Thalia | 53 |  | 1413.3333 |  |  | 24 | 10766581682 | 1 | 1 | 2026-01-13 | 2026-02-05 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/nN2z9K3xd47OEEnhn5pkzrMPOV0lDaq5 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/lbQYGz62nqJeDDyt6qL9wr4P3AZDBjNR | Click me | Not Sent |  | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=10766581682%20-%201101%20Carrie%20Lane%20Apt.%207%20Marseilles%20IL%2061341&text_mkw2a9my=10766581682&text_mkw2sbhy=1101%20Carrie%20Lane%20Apt.%207%20Marseilles%20IL%2061341 | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=10766581682%20-%201101%20Carrie%20Lane%20Apt.%207%20Marseilles%20IL%2061341&text_mkw2a9my=10766581682&text_mkw2sbhy=1101%20Carrie%20Lane%20Apt.%207%20Marseilles%20IL%2061341 |  | Not Done |  | 1101 Carrie Lane Apt. 7 Marseilles IL 61341 | 0.72, 2.0, 3.08, 0.55 | 10766586554 | 1101 Carrie Lane Apt. 7 Marseilles IL 61341 | Mile One, LLC | gentry@tcgpm.us | 1 | 1 | 0 | gentry@tcgpm.us | Approved |  | Not Done | Build Estimate | Build Change Order | At **1101 Carrie Lane Apt. 7, Marseilles, IL 61341**, this turnover focuses on correcting minor interior wear and improving day-to-day condition. Scope includes **wall patching and paint touch-ups** in the living room, dining room, hallway, and bedroom, plus **touch-up painting on the entry door**. This will address scuffs, small surface defects, and uneven appearance so the unit shows clean and consistent. The turnover also includes **basic removal of leftover items/debris** from the living room floor and kitchen sink areas, and **bathroom re-caulking** (top of countertop and base of tub). These items help restore cleanliness and improve moisture protection at wet-area seams. Material Cost: **$37.00** Labor Cost: **$210.00** Total Estimated Cost: **$247.00** **Materials (itemized):** - Paint: **$25.00** - Caulk: **$12.00** Tenant Billed Back (included above): - Tenant billed labor: **$0.00** - Tenant billed material: **$0.00** - Total billed back to tenant: **$0.00** | Send Estimate to Owner |  |  | 2026-01-19 | Send CO Email |  | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | None | None | - Caulk — 1 (UOM N/A) — SKU/Model: N/A - Paint — 1 (UOM N/A) — SKU/Model: N/A |  | Cost Calculator | Calculated | Calculated | Nordstrom | 210 | 37 | 247 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=10766581682&decision=approved | CO Manual Approval ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=10766581682&decision=approved | Yes | 800 | 0 | 0 | 11226036221 | Created | 1101 Carrie Lane Apt. 7 Marseilles IL 61341, 1101 Carrie Lane Apt. 7 Marseilles IL 61341 | 2026-01-29 | Light |  | 10766581682
1413 Adams St Ottawa, IL 61350 |  |  |  | 2025-10-16 | 2026-02-20 | Konnor Homa, Abigail Long | homakonnor23@gmail.com |  |  | 18155012851 | 2025-11-30 | v |  | v | 1730 N Farnsworth Ave. Unit 1 Aurora, IL 60505 | Moving to a different town | [5 empty] | 5 |  | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/0252088f1d594db7bd010e0346c5da16 | Send Email | 2025-12-08 | 2026-02-11 | 2026-02-11 | NA |  |  |  | v | 1600 | New Pics Needed | Ready To Market | Deposit Received | Townhouse |  |  | Yes | Add | Full Service | 1413 Adams St Ottawa, IL 61350TO/General Maintenance, 1413 Adams St Ottawa, IL 61350TO/Tenant Billed, 1413 Adams St Ottawa, IL 61350TO/Painting, 1413 Adams Tenant cleanout | Completed, Completed, Completed, Completed | 2.15, 0.33, 1.5, 3.0, 3.32, 5.67, 2.03, 3.1, 1.95, 0.45, 2.67, 2.0, 1.63, 1.67, 0.83, 3.17, 1.75, 5.08, 4.82, 1.67, 4.7, 2.25, 7.48, 5.0, 1.75, 1.42, 1.42, 1.42 | 532.5, 2115 | 554, 547, 0, 0 | 000, 00 | 42 |  | 2026-02-09 | 2026-02-12 | 8.729 | 1 | Oct 16, 2025 12:31 PM | Thalia | 82 |  | 4373.3333 |  |  | 65 | 18203020378 | 1 | 1 | 2025-12-11 | 2026-01-26 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/2VMLonxWde7zwwWUwwNjoXR8lgN6GpAm | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/nzePQO2YK4Jjll5imnl4NXGvx1alNkW5 | Click me | Not Sent | NA | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18203020378%20-%201413%20Adams%20St%20Ottawa,%20IL%2061350&text_mkw2a9my=18203020378&text_mkw2sbhy=1413%20Adams%20St%20Ottawa,%20IL%2061350 | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18203020378%20-%201413%20Adams%20St%20Ottawa%2C%20IL%2061350&text_mkw2a9my=18203020378&text_mkw2sbhy=1413%20Adams%20St%20Ottawa%2C%20IL%2061350 | 1413 Adams St Ottawa, IL 61350, 1413 Adams St Ottawa, IL 61350, 1413 Adams St Ottawa, IL 61350, 1413 Adams St Ottawa, IL 61350 | Not Done |  | 1413 Adams Street Ottawa IL 61350, 1413 Adams St Ottawa, IL 61350 | 2.03, 2.15, 3.1, 0.45, 2.67, 1.95, 2.0, 0.33, 1.5, 1.63, 1.67, 3.17, 1.75, 5.08, 4.82, 1.67, 2.25, 4.7, 7.48, 5.0, 1.75, 0.83, 3.0, 5.67, 3.32, 2.03, 2.15, 3.1, 0.45, 2.67, 1.95, 2.0, 0.33, 1.5, 1.63, 1.67, 3.17, 1.75, 5.08, 4.82, 1.67, 2.25, 4.7, 7.48, 5.0, 1.75, 0.83, 3.0, 5.67, 3.32 | 18194959181, 18203021027 | 1413 Adams Street Ottawa IL 61350 | Mile One-Windsor Court Series | gentry@tcgpm.us | 2 | 1 | 1 | gentry@tcgpm.us | Approved | Approved | Picture in Rentvine | Build Estimate | Build Change Order | At 1413 Adams St, the turnover scope begins with unit‐wide cleanout and debris removal (including dumpster rental), carpet cleaning and spot repair, and replacement of all window coverings. Flooring is secured and patched where needed. These measures restore a clean, hazard‐free living environment. Walls and trim receive fresh paint throughout: the main floor, bedrooms, stairwell wall, and laundry/bathroom entry. Hardware and fixtures are serviced or replaced—hardwired smoke detector, thermostat, light bulbs, toilet paper holder—and plumbing adjustments address a leaking laundry hookup, bidet removal, and loose bathroom baseboard. Material cost: $1,101 Labor cost: $2,465 Total estimated cost: $3,566 Materials provided: • Dumpster rental: $380 • Paint: $522 • Blinds (6 units): $103 • Vertical blinds (25 units): $64 • Light bulbs (5 units): $4 • Toilet paper holder: $28 Tenant‐billed labor: $2,115 Tenant‐billed materials: $547 | Send Estimate to Owner |  |  | 2025-12-22 | Send CO Email | ### Change Order Summary – 1413 Adams St, Ottawa, IL 61350 This change order covers additional turnover work needed to make the unit rent-ready, including removal of tenant left-behind items and debris (including a dumpster), full repainting of the main floor plus additional targeted repainting (bedroom and stair area), carpet cleaning and a small carpet patch repair, and addressing several punch-list items. It also includes basic electrical and plumbing-related corrections such as replacing a missing hardwired smoke detector, reinstalling a thermostat, replacing missing light bulbs, removing a bidet attachment, securing a loose bathroom baseboard, replacing broken/missing window blinds, fixing leaking laundry water hookups, replacing an upstairs toilet paper holder, and added painting hours. **Material Cost:** $1,101.00 **Labor Cost:** $2,647.50 **Total Estimated Cost:** $3,748.50 ### Materials List (with individual costs) - Dumpster for debris: **$380.00** - Paint (3): **$522.00** - Blinds (x6): **$103.00** - Vertical blinds (x25): **$64.00** - Bulbs (x5): **$4.00** - Toilet paper holder: **$28.00** | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | None | None | - Dumpster for debris, 1 ea - Paint, 3 ea - Blinds (x6), 1 ea - Vertical blinds (x25), 1 ea - Bulbs (x5), 1 ea - Toilet paper holder, 1 ea |  | Cost Calculator | Calculated | Calculated | Nordstrom | 2465 | 1101 | 3566 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=18203020378&decision=approved | Approve CO ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=18203020378&decision=approved | Yes | 1600 | 2115 | 547 | 11211899712 | Created | 1413 Adams St Ottawa, IL 61350 | 2025-12-26 | Standard |  | 18203020378
1400 Kansas Street Apt A Ottawa IL 61350 |  |  |  | 2025-10-27 | 2026-03-03 | Stephanie Marie Escobar |  |  |  |  | 2025-11-30 | v |  | v | 838 Congress St #3 | I need more space for my family. | [7 empty] | Keys Received |  | Move-Out Checklist - https://superform.spot-nik.com/instance/5711717238ed4227a6077438ca6df123 | Send Email | 2025-12-02 | 2026-01-27 | 2026-01-27 | 2374831 sentrillock |  |  |  | v | 825 | New Pictures In Rentvine | Ready To Market | Deposit Received |  |  |  | Yes | Add | Full Service | 1400 Kansas Street Apt A Ottawa IL 61350TO/Painting, 1400 Kansas Street Apt A Ottawa IL 61350TO/General Maintenance, 1400 Kansas Street Apt A Ottawa IL 61350TO/Tenant Billed, 1400Kansas/TO/Final Maintenance | Completed, Completed, Completed, Completed | 3.0, 1.25, 2.0, 4.0, 0.17, 3.33, 1.17, 0.33, 1.67, 2.0, 0.33, 1.42, 1.63, .6, .43 | 1189, 130 | 0, 149, 126, 0 | 00, 0 | 25 | 93.32 | 2026-01-23 | 2026-02-17 | 23.729 | 21 | Oct 27, 2025 9:33 PM | Thalia | 93 |  | 2557.5 |  |  | 56 | 18283758558 | 1 | 1 | 2025-12-04 | 2026-01-16 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/Rxnqdjo8Mm7dYYAHMMj4aXyewpOAVla0 | Report - https://portfolio.zinspector.com/report/openSharedDocumentReport/y3R1odap8qX0xxZFy6nbAXNMegBx0YzG | Click me | Not Sent | front door | https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18283758558%20-%201400%20Kansas%20Street%20Apt%20A%20Ottawa%20IL%2061350&text_mkw2a9my=18283758558&text_mkw2sbhy=1400%20Kansas%20Street%20Apt%20A%20Ottawa%20IL%2061350 | Add Transcript - https://forms.monday.com/forms/79c1db40b274da94834f961641a2706e?r=use1&name=18283758558%20-%201400%20Kansas%20Street%20Apt%20A%20Ottawa%20IL%2061350&text_mkw2a9my=18283758558&text_mkw2sbhy=1400%20Kansas%20Street%20Apt%20A%20Ottawa%20IL%2061350 | 1400 Kansas Street Apt A Ottawa IL 61350, 1400 Kansas Street Apt A Ottawa IL 61350, 1400 Kansas Street Apt A Ottawa IL 61350, 1400 Kansas Street Apt A Ottawa IL 61350, 1400 Kansas Street Apt A Ottawa IL 61350 | Not Done |  | 1400 Kansas Street Apt A Ottawa IL 61350 | 0.33, 1.67, 3.0, 1.25, 2.0, 2.0, 1.42, 0.33, 4.0, 0.17, 3.33, 1.17, 1.63, .6, .43 | 18283758735 | 1400 Kansas Street Apt A Ottawa IL 61350 | KPON Properties, LLC | keith@kponproperties.com | 1 | 1 | 0 | keith@kponproperties.com | Approved |  | Picture in Rentvine | Build Estimate | Build Change Order | This turnover scope restores the unit to market-ready condition through targeted cleaning, repairs and refinishing. In the bathroom, we’ll remove cobwebs, deep-clean surfaces, patch drywall cracks, recaulk all wet areas, repair the exhaust fan, secure loose fixtures and replace the toilet internals. Walls, ceilings, baseboards, doors and window frames will be repainted to freshen finishes and prevent future damage. Throughout the rest of the apartment, we’ll clean light globes, replace burned-out bulbs, remove debris from the microwave, and touch up paint on walls, trim and doors in the kitchen, living room, master bedroom and closet. All hardware (towel rack, window blinds) will be secured or replaced—four new blinds restore privacy and light control. Material cost: $275.00 Labor cost: $1,319.50 Total estimated cost: $1,594.50 Breakdown of materials: • Toilet internals – $23.00 • Caulk – $12.00 • Paint – $114.00 • Blinds (4 units) – $126.00 Amounts billed back to tenant (reduces owner’s portion): • Tenant-billed labor – $130.00 • Tenant-billed materials – $126.00 | Send Estimate to Owner |  |  | 2025-12-09 | Send CO Email |  | prodesk_1977@homedepot.com | perubuildingmaterials@menards.com | Built | Build Material List | None | None | None | - Toilet internals: 1 ea - Caulk: 1 ea - Paint: 3 ea - Blinds (x4): 4 ea |  | Cost Calculator | Calculated | Calculated | KPON | 1319.5 | 275 | 1594.5 | Manual Approval¦ Create WO's - https://hook.us1.make.com/60dtv9os30d9pa4uf70qcg2jpt5amcyt?item_id=18283758558&decision=approved | CO Manual Approval ¦ Create WO - https://hook.us1.make.com/9vx7a8y6zw2y757sxbfpy79w7nfq0jnj?item_id=18283758558&decision=approved | Yes | 825 | 130 | 126 | 11226033326 | Created | 1400 Kansas Street Apt A Ottawa IL 61350 | 2025-12-20 | Standard |  | 18283758558
|  |  |  | 2025-08-28 to 2025-12-12 | 2025-11-03 to 2026-03-03 | [5 empty] | 2025-09-18 to 2026-01-01 | 3/16 | 1/16 | 3/16 | [7 empty] | 4/5 | [5 empty] | 2025-09-18 to 2026-01-12 | 2025-11-03 to 2026-02-11 | 2025-11-03 to 2026-02-11 |  | 0/16 | 2/16 | 0/16 | 4/16 | =SUM(AK9:AK24) | [15 empty] | =SUM(BA9:BA24) | 1174.2971 | 2025-11-03 to 2026-02-09 | 2025-11-03 to 2026-02-17 | 43.7288 | 216 |  |  | 998 | 375.1857 | 33305.8333 | 15004.4061 | null | 953 |  | =SUM(BP9:BP24) | =SUM(BQ9:BQ24) | 2025-09-19 to 2026-01-13 | 2025-10-30 to 2026-02-05 | [5 empty] | null | [23 empty] | 2025-10-13 to 2026-01-19 | [15 empty] | =SUM(DM9:DM24) | =SUM(DN9:DN24) | 19565.265 |  |  |  | =SUM(DS9:DS24) | =SUM(DT9:DT24) | =SUM(DU9:DU24) |  |  |  | 2025-10-30 to 2026-01-29